## Read me first
BIM MULTI-SITE DELIVERY TRACKER
SHEETS
1. Sites | The register. One row per site code, with its start and target submission dates.
2. Task Template | Two tables. Table 1 is the standard category and task framework every site starts from. Table 2 is the standard prerequisite list.
3. One sheet per site | Named exactly as the site code. Three tables: the task list with weekly status, this site's prerequisites, and the waiting-on log.
THE ID SYSTEM - THIS IS THE SPINE
C010, C020 ... | Category IDs. Numbered in tens so you can insert a category later without renumbering.
T030-01, T030-02 ... | Task IDs. The number after T matches the category the task sits under, so a task ID tells you where it belongs without looking anything up. Ready to reuse as a 4D WBS code.
P01, P02 ... | Prerequisite IDs, per site.
PT01, PT02 ... | Prerequisite IDs on the template sheet.
R1, R2 ... | Resource codes. Never real names.
L01, L02 ... | Waiting-on log entries.
Why IDs | Every cross-reference uses an ID, never a name. Rename a task and nothing breaks.
PRIVACY - READ PROPERLY
The rule | NO client names, site names, addresses, contractor names or people's names anywhere in this workbook.
Codes only | Sites are A-01. People are R1, R2. Keep a SEPARATE private file mapping codes to real names and site details. Never give that file to the app and never upload it anywhere.
The easy mistake | Task and prerequisite names are free text and ARE sent to the AI. Write 'Draft model - substructure'. Do NOT write 'Substructure at Al Wasl Villa 3'. The app scans for names and places that look real and will warn you, but it cannot catch everything - you are the check.
STATUS VALUES
Not started | Not begun. Nobody is on it.
WIP | Actively being worked on this week.
Blocked | Stopped by something INSIDE your team's control - rework, resource pulled away, tool problem.
Waiting on | Stopped by something OUTSIDE your team - client, another discipline, supplier, survey.
Blocked vs Waiting on | The difference matters: one you fix yourself, the other you must chase someone for. If you use them interchangeably the bottleneck report becomes meaningless. EITHER of them requires a row in Table 3 saying why.
Finished | Meets the Definition of done for its category, on the Task Template sheet.
N/A | Does not apply to this site. Excluded from percentages rather than counted as incomplete.
Blank | The task did not exist that week. This is how scope growth is measured - do not backfill blanks.
WEEK COLUMNS
Two header rows | The upper row is the week number (W01, W02). The lower row is the date that week ENDS. Both are read by the app; use whichever you prefer when reading.
Adding weeks | Add columns to the right and continue the pattern. The app finds them because the header is a date.
CATEGORY ROWS
Grey rows | Each category has its own row with its own weekly status. That is YOUR overall read of the category, which may differ from the arithmetic of its tasks - and where it does, that gap is itself worth seeing. The app reports both.
REGULAR vs ADDITIONAL
Regular | Scope agreed at kickoff.
Additional | Added later. Fill in 'Date added'. This is your record of how much the job grew and when.
CELLS YOU FILL IN | Anything on a pale yellow background.

## Sites
SITE REGISTER
Master timeline view. 'Detail sheet' must match a tab name exactly. Codes only - no real names.
Site code | Description (generic) | Package type | Wave / batch | Start date | Target submission | Actual submission | Current category | Status | Priority | Coordinator (R code) | Detail sheet | Notes
A-01 | Type B unit | Full BIM | Wave 1 | 2026-01-05 | 2026-04-03 |  | Draft Modelling | In progress | High | R1 | A-01
A-02 | Type B unit | Full BIM | Wave 1 | 2026-01-19 | 2026-04-17 |  | Initial setup | In progress | Medium | R1 | A-02
A-03 | Type C unit | Model only | Wave 2 | 2026-03-02 | 2026-05-29 |  | Initial setup | Not started | Medium | R6 | A-03
Note on D4: Sites in the same wave run in parallel and compete for the same people. The app uses this to spot resource clashes.
Note on F4: Without this date the app cannot tell you whether a site will make its submission.

## Task Template
STANDARD FRAMEWORK
Edit here once and every new site starts from it. The process is iterative - categories recur - so Order is a reading order, not a rigid sequence.
TABLE 1 - TASK FRAMEWORK
Order | ID | Category | Standard task / scope item | Definition of done (category) | Typical duration (days) | Applies to | Default prerequisites (PT IDs)
10 | C010 | Initial setup |  | Project set up and ready to work in | 3 | All | PT02,PT03,PT07,PT12
| T010-01 | Initial setup | Create project folder and CDE structure |  |  | All
| T010-02 | Initial setup | Apply project template file |  |  | All
| T010-03 | Initial setup | Set shared coordinates and survey point |  |  | All
20 | C020 | Prerequisite preparation |  | Everything needed to start production is in hand and usable | 5 | All | PT01,PT04,PT05,PT06,PT08,PT15
| T020-01 | Prerequisite preparation | Confirm Revit families available for scope |  |  | All
| T020-02 | Prerequisite preparation | Confirm base survey / point cloud usable |  |  | All
| T020-03 | Prerequisite preparation | Confirm reference drawings received |  |  | All
| T020-04 | Prerequisite preparation | Confirm standards and naming convention issued |  |  | All
30 | C030 | Draft Modelling |  | First-pass model built from available information | 10 | All | PT01
| T030-01 | Draft Modelling | Draft model - substructure |  |  | Struct
| T030-02 | Draft Modelling | Draft model - superstructure |  |  | Struct
| T030-03 | Draft Modelling | Draft model - architectural envelope |  |  | Arch
| T030-04 | Draft Modelling | Draft model - MEP primary routes |  |  | MEP
40 | C040 | Draft sheet work |  | First-pass sheets generated from the draft model | 5 | All | PT11
| T040-01 | Draft sheet work | Set up sheets and views |  |  | All
| T040-02 | Draft sheet work | Draft general arrangement sheets |  |  | All
50 | C050 | Initial Design |  | Design intent developed and issued for comment | 8 | All | PT14
| T050-01 | Initial Design | Develop design option |  |  | All
| T050-02 | Initial Design | Internal design review |  |  | All
| T050-03 | Initial Design | Issue design for comment |  |  | All
60 | C060 | Design Revision |  | Design changes agreed and issued; model and sheets know what to follow | 5 | All
| T060-01 | Design Revision | Receive and log design revision |  |  | All
| T060-02 | Design Revision | Assess revision impact on model and sheets |  |  | All
| T060-03 | Design Revision | Issue revised design information to team |  |  | All
70 | C070 | Modelling Revise |  | Model updated to reflect the revised design | 8 | All
| T070-01 | Modelling Revise | Update model to developed design |  |  | All
| T070-02 | Modelling Revise | Implement design revision in model |  |  | All
| T070-03 | Modelling Revise | Add secondary elements |  |  | All
80 | C080 | Sheet work Updates |  | Sheets brought back in line with the revised model | 5 | All
| T080-01 | Sheet work Updates | Update sheets to revised model |  |  | All
| T080-02 | Sheet work Updates | Update annotation and dimensions |  |  | All
| T080-03 | Sheet work Updates | Update revision clouds and revision schedule |  |  | All
90 | C090 | Other Deliverables preparation |  | Schedules, reports and non-drawing outputs produced | 4 | All
| T090-01 | Other Deliverables preparation | Produce schedules |  |  | All
| T090-02 | Other Deliverables preparation | Produce quantity extract |  |  | All
100 | C100 | Final Tuning of individual discipline deliverables |  | Each discipline package internally complete and consistent | 5 | All
| T100-01 | Final Tuning of individual discipline deliverables | Discipline self-check and cleanup |  |  | All
| T100-02 | Final Tuning of individual discipline deliverables | Purge and audit model |  |  | All
110 | C110 | Cross Discipline check |  | Disciplines coordinated; clash report issued | 4 | All | PT09,PT10
| T110-01 | Cross Discipline check | Federate models |  |  | All
| T110-02 | Cross Discipline check | Run clash detection |  |  | All
| T110-03 | Cross Discipline check | Clash review meeting |  |  | All
120 | C120 | Cross discipline check comments update |  | All coordination comments resolved in model and sheets | 4 | All
| T120-01 | Cross discipline check comments update | Resolve priority 1 clashes |  |  | All
| T120-02 | Cross discipline check comments update | Re-run clash detection |  |  | All
130 | C130 | QA |  | QA checklist signed off by someone other than the author | 3 | All
| T130-01 | QA | Model standards audit |  |  | All
| T130-02 | QA | Drawing check |  |  | All
| T130-03 | QA | Sign off QA checklist |  |  | All
140 | C140 | Comments update |  | Every client/reviewer comment closed or formally disputed | 5 | All | PT13
| T140-01 | Comments update | Log received comments |  |  | All
| T140-02 | Comments update | Update model and sheets for comments |  |  | All
| T140-03 | Comments update | Return commented log |  |  | All
150 | C150 | Submission |  | Transmittal issued and receipt confirmed | 2 | All
| T150-01 | Submission | Export and package deliverables |  |  | All
| T150-02 | Submission | Issue transmittal |  |  | All
TABLE 2 - PREREQUISITE TEMPLATE
Prereq ID | Prerequisite | Why it is needed | Usually provided by | Needed before (category ID)
PT01 | Revit families / content library ready for the scope | Modelling cannot start without the correct parametric content | BIM lead | C030
PT02 | Project template file issued and applied | Sets views, filters, standards; retrofitting it later is rework | BIM lead | C010
PT03 | Shared coordinates / survey point confirmed | Models will not federate for clash detection without it | Survey / BIM lead | C010
PT04 | Base survey or point cloud received and readable | Existing conditions basis for all modelling | Client / survey | C020
PT05 | Client brief and scope confirmation | Defines what is in and out of scope for this site | Client | C020
PT06 | Reference drawings received | Design basis for draft modelling | Client / design team | C020
PT07 | Standards and naming convention document issued | Determines file, view and element naming; late changes force a rename pass | BIM lead | C010
PT08 | Level of information need / LOD specification agreed | Defines when modelling is 'finished' | BIM lead / client | C020
PT09 | Other disciplines' models available for federation | Cross-discipline check cannot run without them | Other task teams | C110
PT10 | Clash rule set / matrix agreed | Determines which clashes are reported and at what priority | BIM lead | C110
PT11 | Sheet titleblock and drawing list agreed | Sheet work cannot be set up without it | BIM lead | C040
PT12 | CDE access and permissions granted for the team | Nothing can be shared or issued without it | Information manager | C010
PT13 | Client comment log received | Comments update cannot start until comments arrive | Client | C140
PT14 | Authority / planning requirements confirmed | Can invalidate design work if it arrives late | Client / consultant | C050
PT15 | Resource allocated and available | A task with nobody on it will not move regardless of readiness | Resource manager | C020
Note on A5: Numbered in tens so a new category can be inserted without renumbering everything.
Note on E5: Write this properly. If two modellers disagree about what 'finished' means, every percentage in the app is meaningless.
Note on A66: These IDs are the master list. On a site sheet you give the site's own prerequisites P01, P02... and point each back to the template ID it came from.

## A-01
SITE A-01
Site code | Start date | Target submission | Coordinator | Package | Wave
A-01 | 2026-01-05 | 2026-04-03 | R1 | Full BIM | Wave 1
Keep task and prerequisite names generic - they are sent to the AI. Statuses: Not started / WIP / Blocked / Waiting on / Finished / N/A
TABLE 1 - TASK LIST AND WEEKLY STATUS
[8 empty] | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
Task ID | Category | Discipline | Task / component | Weight | Type | Date added | Target week | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | Completed - week | Completed - date | Responsible (R code) | Prerequisite (P IDs) | Depends on (Task IDs)
C010 | Initial setup | All | [Category] Initial setup |  |  |  |  | 2026-01-11: Finished; 2026-01-18: Finished; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished
T010-01 | Initial setup | All | Create project folder and CDE structure | 1 | Regular |  | 1 | 2026-01-11: Finished; 2026-01-18: Finished; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished | 1 | 2026-01-09 | R1
T010-02 | Initial setup | All | Apply project template file | 1 | Regular |  | 1 | 2026-01-11: Finished; 2026-01-18: Finished; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished | 1 | 2026-01-09 | R1 | P02
T010-03 | Initial setup | All | Set shared coordinates and survey point | 1 | Regular |  | 1 | 2026-01-11: Finished; 2026-01-18: Finished; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished | 1 | 2026-01-09 | R1 | P03 | T010-02
C020 | Prerequisite preparation | All | [Category] Prerequisite preparation |  |  |  |  | 2026-01-11: WIP; 2026-01-18: WIP; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished
T020-01 | Prerequisite preparation | All | Confirm Revit families available for scope | 1 | Regular |  | 2 | 2026-01-11: WIP; 2026-01-18: Finished; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished | 2 | 2026-01-16 | R1 | P01
T020-02 | Prerequisite preparation | All | Confirm base survey / point cloud usable | 1 | Regular |  | 2 | 2026-01-11: Waiting on; 2026-01-18: Finished; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished | 2 | 2026-01-16 | R2 | P04
T020-03 | Prerequisite preparation | All | Confirm reference drawings received | 1 | Regular |  | 2 | 2026-01-11: WIP; 2026-01-18: Finished; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished | 2 | 2026-01-16 | R1
T020-04 | Prerequisite preparation | All | Confirm standards and naming convention issued | 1 | Regular |  | 2 | 2026-01-11: WIP; 2026-01-18: WIP; 2026-01-25: Finished; 2026-02-01: Finished; 2026-02-08: Finished; 2026-02-15: Finished | 3 | 2026-01-23 | R1 | P07
C030 | Draft Modelling | All | [Category] Draft Modelling |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: WIP; 2026-02-01: WIP; 2026-02-08: WIP; 2026-02-15: WIP
T030-01 | Draft Modelling | Struct | Draft model - substructure | 3 | Regular |  | 4 | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: WIP; 2026-02-01: WIP; 2026-02-08: Finished; 2026-02-15: Finished | 5 | 2026-02-06 | R2 | P01 | T020-01,T020-02
T030-02 | Draft Modelling | Struct | Draft model - superstructure | 5 | Regular |  | 5 | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: WIP; 2026-02-08: WIP; 2026-02-15: WIP |  |  | R2 | P01 | T030-01
T030-03 | Draft Modelling | Arch | Draft model - architectural envelope | 3 | Regular |  | 5 | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: WIP; 2026-02-08: WIP; 2026-02-15: Finished | 6 | 2026-02-13 | R3 |  | T030-01
T030-04 | Draft Modelling | MEP | Draft model - MEP primary routes | 3 | Regular |  | 6 | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Waiting on; 2026-02-15: Waiting on |  |  | R5 | P05 | T030-03
C040 | Draft sheet work | All | [Category] Draft sheet work |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: WIP
T040-01 | Draft sheet work | All | Set up sheets and views | 2 | Regular |  | 6 | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: WIP |  |  | R3 | P07 | T030-02
T040-02 | Draft sheet work | All | Draft general arrangement sheets | 3 | Regular |  | 7 | [28 empty] | R3 | P07 | T040-01
C050 | Initial Design | All | [Category] Initial Design |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T050-01 | Initial Design | All | Develop design option | 3 | Regular |  | 7 | [28 empty] | R4 |  | T030-02
T050-02 | Initial Design | All | Internal design review | 1 | Regular |  | 8 | [28 empty] | R4 |  | T050-01
T050-03 | Initial Design | All | Issue design for comment | 1 | Regular |  | 8 | [28 empty] | R4 |  | T050-02
C060 | Design Revision | All | [Category] Design Revision |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T060-01 | Design Revision | All | Receive and log design revision | 1 | Regular
T060-02 | Design Revision | All | Assess revision impact on model and sheets | 1 | Regular
T060-03 | Design Revision | All | Issue revised design information to team | 1 | Regular
C070 | Modelling Revise | All | [Category] Modelling Revise |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T070-01 | Modelling Revise | All | Update model to developed design | 1 | Regular
T070-02 | Modelling Revise | All | Implement design revision in model | 1 | Regular
T070-03 | Modelling Revise | All | Add secondary elements | 1 | Regular
C080 | Sheet work Updates | All | [Category] Sheet work Updates |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T080-01 | Sheet work Updates | All | Update sheets to revised model | 1 | Regular
T080-02 | Sheet work Updates | All | Update annotation and dimensions | 1 | Regular
T080-03 | Sheet work Updates | All | Update revision clouds and revision schedule | 1 | Regular
C090 | Other Deliverables preparation | All | [Category] Other Deliverables preparation |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T090-01 | Other Deliverables preparation | All | Produce schedules | 1 | Regular
T090-02 | Other Deliverables preparation | All | Produce quantity extract | 1 | Regular
T090-03 | Other Deliverables preparation | Struct | Produce clash summary report | 2 | Additional | 2026-02-09 | 9 | 2026-02-15: Not started |  |  | R2 |  | T030-02
C100 | Final Tuning of individual discipline deliverables | All | [Category] Final Tuning of individual discipline deliverables |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T100-01 | Final Tuning of individual discipline deliverables | All | Discipline self-check and cleanup | 1 | Regular
T100-02 | Final Tuning of individual discipline deliverables | All | Purge and audit model | 1 | Regular
C110 | Cross Discipline check | All | [Category] Cross Discipline check |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T110-01 | Cross Discipline check | All | Federate models | 1 | Regular |  | 10 | [28 empty] | R1 |  | T030-02,T030-03,T030-04
T110-02 | Cross Discipline check | All | Run clash detection | 2 | Regular |  | 10 | [28 empty] | R1 | P06 | T110-01
T110-03 | Cross Discipline check | All | Clash review meeting | 1 | Regular
C120 | Cross discipline check comments update | All | [Category] Cross discipline check comments update |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T120-01 | Cross discipline check comments update | All | Resolve priority 1 clashes | 1 | Regular
T120-02 | Cross discipline check comments update | All | Re-run clash detection | 1 | Regular
C130 | QA | All | [Category] QA |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T130-01 | QA | All | Model standards audit | 2 | Regular |  | 11 | [28 empty] | R1 |  | T110-02
T130-02 | QA | All | Drawing check | 1 | Regular
T130-03 | QA | All | Sign off QA checklist | 1 | Regular
C140 | Comments update | All | [Category] Comments update |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T140-01 | Comments update | All | Log received comments | 1 | Regular
T140-02 | Comments update | All | Update model and sheets for comments | 1 | Regular
T140-03 | Comments update | All | Return commented log | 1 | Regular
C150 | Submission | All | [Category] Submission |  |  |  |  | 2026-01-11: Not started; 2026-01-18: Not started; 2026-01-25: Not started; 2026-02-01: Not started; 2026-02-08: Not started; 2026-02-15: Not started
T150-01 | Submission | All | Export and package deliverables | 1 | Regular
T150-02 | Submission | All | Issue transmittal | 1 | Regular |  | 12 | [28 empty] | R1 |  | T130-01
TABLE 2 - PREREQUISITES FOR THIS SITE | bar: 2026-01-11
Prereq ID | Prerequisite | From template (PT ID) | Needed for (Task IDs) | Provided by (R code / party) | Required by week | Status | Date received | 2026-01-11: Notes
P01 | Revit families for structural scope | PT01 | T030-01,T030-02 | R1 | 2 | Received | 2026-01-09 | bar: 2026-01-11
P02 | Project template file | PT02 | T010-02 | R1 | 1 | Received | 2026-01-07 | bar: 2026-01-11
P03 | Shared coordinates confirmed | PT03 | T010-03 | R1 | 1 | Received | 2026-01-08 | bar: 2026-01-11
P04 | Point cloud for existing structure | PT04 | T020-02 | R4 | 2 | Received | 2026-01-15 | bar: 2026-01-11
P05 | Architectural ceiling void zones confirmed | PT06 | T030-04 | R5 | 4 | Outstanding | bar: 2026-01-11
P06 | Clash rule matrix agreed | PT10 | T110-02 | R1 | 8 | Outstanding | bar: 2026-01-11
P07 | Drawing list and titleblock | PT11 | T040-01 | R1 | 3 | Received | 2026-01-22 | bar: 2026-01-11
TABLE 3 - WAITING ON / BLOCKED LOG | bar: 2026-01-11 to 2026-01-18
Log ID | Week (W no) | Task ID | Status raised | Reason | Waiting on (R code / party) | Raised date | Expected clear date | 2026-01-11: Cleared date; 2026-01-18: Notes
L01 | 1 | T020-02 | Waiting on | Point cloud not yet delivered by survey team | R4 (survey) | 2026-01-05 | 2026-01-12 | 2026-01-11: 2026-01-15; 2026-01-18: Cleared 3 days late
L02 | 5 | T030-04 | Waiting on | Architectural ceiling void zones not confirmed - cannot route MEP | R5 / Arch team | 2026-02-02 | 2026-02-09 | 2026-01-18: Still open - blocking MEP draft model
Note on A8: T + category number + sequence, e.g. T030-01 sits under category C030. Reusable as a 4D WBS code.
Note on D8: KEEP GENERIC. Sent to the AI. 'Draft model - substructure', not a real site name.
Note on E8: Optional rough size, default 1. Without it a one-hour task counts the same as a week's modelling.
Note on F8: Regular = agreed at kickoff. Additional = added later; fill in Date added.
Note on H8: The week number you expect this finished. Without it nothing can be reported as late.
Note on I8: Upper row is the week number, this row is the date the week ENDS. Overwrite with your real dates and add columns to the right as the job runs.
Note on AI8: Fill in when the task is done. The app cross-checks this against the week columns and flags any disagreement.
Note on AL8: Prerequisite IDs from Table 2 below, comma separated. e.g. P01,P04
Note on AM8: Task IDs this one cannot start before, comma separated. e.g. T030-01,T030-02
Note on A71: Give each prerequisite a P number for this site. Reference these IDs in the 'Prerequisite (P IDs)' column of Table 1.
Note on A88: Every time you put Blocked or Waiting on in a week cell in Table 1, add a row here saying why. This table is where the bottleneck report comes from - without it the app can only say 'something is stuck', not what.

## A-02
SITE A-02
Site code | Start date | Target submission | Coordinator | Package | Wave
A-02 | 2026-01-19 | 2026-04-17 | R1 | Full BIM | Wave 1
Keep task and prerequisite names generic - they are sent to the AI. Statuses: Not started / WIP / Blocked / Waiting on / Finished / N/A
TABLE 1 - TASK LIST AND WEEKLY STATUS
[8 empty] | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
Task ID | Category | Discipline | Task / component | Weight | Type | Date added | Target week | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | Completed - week | Completed - date | Responsible (R code) | Prerequisite (P IDs) | Depends on (Task IDs)
C010 | Initial setup | All | [Category] Initial setup
T010-01 | Initial setup | All | Create project folder and CDE structure | 1 | Regular
T010-02 | Initial setup | All | Apply project template file | 1 | Regular
T010-03 | Initial setup | All | Set shared coordinates and survey point | 1 | Regular
C020 | Prerequisite preparation | All | [Category] Prerequisite preparation
T020-01 | Prerequisite preparation | All | Confirm Revit families available for scope | 1 | Regular
T020-02 | Prerequisite preparation | All | Confirm base survey / point cloud usable | 1 | Regular
T020-03 | Prerequisite preparation | All | Confirm reference drawings received | 1 | Regular
T020-04 | Prerequisite preparation | All | Confirm standards and naming convention issued | 1 | Regular
C030 | Draft Modelling | All | [Category] Draft Modelling
T030-01 | Draft Modelling | Struct | Draft model - substructure | 1 | Regular
T030-02 | Draft Modelling | Struct | Draft model - superstructure | 1 | Regular
T030-03 | Draft Modelling | Arch | Draft model - architectural envelope | 1 | Regular
T030-04 | Draft Modelling | MEP | Draft model - MEP primary routes | 1 | Regular
C040 | Draft sheet work | All | [Category] Draft sheet work
T040-01 | Draft sheet work | All | Set up sheets and views | 1 | Regular
T040-02 | Draft sheet work | All | Draft general arrangement sheets | 1 | Regular
C050 | Initial Design | All | [Category] Initial Design
T050-01 | Initial Design | All | Develop design option | 1 | Regular
T050-02 | Initial Design | All | Internal design review | 1 | Regular
T050-03 | Initial Design | All | Issue design for comment | 1 | Regular
C060 | Design Revision | All | [Category] Design Revision
T060-01 | Design Revision | All | Receive and log design revision | 1 | Regular
T060-02 | Design Revision | All | Assess revision impact on model and sheets | 1 | Regular
T060-03 | Design Revision | All | Issue revised design information to team | 1 | Regular
C070 | Modelling Revise | All | [Category] Modelling Revise
T070-01 | Modelling Revise | All | Update model to developed design | 1 | Regular
T070-02 | Modelling Revise | All | Implement design revision in model | 1 | Regular
T070-03 | Modelling Revise | All | Add secondary elements | 1 | Regular
C080 | Sheet work Updates | All | [Category] Sheet work Updates
T080-01 | Sheet work Updates | All | Update sheets to revised model | 1 | Regular
T080-02 | Sheet work Updates | All | Update annotation and dimensions | 1 | Regular
T080-03 | Sheet work Updates | All | Update revision clouds and revision schedule | 1 | Regular
C090 | Other Deliverables preparation | All | [Category] Other Deliverables preparation
T090-01 | Other Deliverables preparation | All | Produce schedules | 1 | Regular
T090-02 | Other Deliverables preparation | All | Produce quantity extract | 1 | Regular
C100 | Final Tuning of individual discipline deliverables | All | [Category] Final Tuning of individual discipline deliverables
T100-01 | Final Tuning of individual discipline deliverables | All | Discipline self-check and cleanup | 1 | Regular
T100-02 | Final Tuning of individual discipline deliverables | All | Purge and audit model | 1 | Regular
C110 | Cross Discipline check | All | [Category] Cross Discipline check
T110-01 | Cross Discipline check | All | Federate models | 1 | Regular
T110-02 | Cross Discipline check | All | Run clash detection | 1 | Regular
T110-03 | Cross Discipline check | All | Clash review meeting | 1 | Regular
C120 | Cross discipline check comments update | All | [Category] Cross discipline check comments update
T120-01 | Cross discipline check comments update | All | Resolve priority 1 clashes | 1 | Regular
T120-02 | Cross discipline check comments update | All | Re-run clash detection | 1 | Regular
C130 | QA | All | [Category] QA
T130-01 | QA | All | Model standards audit | 1 | Regular
T130-02 | QA | All | Drawing check | 1 | Regular
T130-03 | QA | All | Sign off QA checklist | 1 | Regular
C140 | Comments update | All | [Category] Comments update
T140-01 | Comments update | All | Log received comments | 1 | Regular
T140-02 | Comments update | All | Update model and sheets for comments | 1 | Regular
T140-03 | Comments update | All | Return commented log | 1 | Regular
C150 | Submission | All | [Category] Submission
T150-01 | Submission | All | Export and package deliverables | 1 | Regular
T150-02 | Submission | All | Issue transmittal | 1 | Regular
TABLE 2 - PREREQUISITES FOR THIS SITE | bar: 2026-01-11
Prereq ID | Prerequisite | From template (PT ID) | Needed for (Task IDs) | Provided by (R code / party) | Required by week | Status | Date received | 2026-01-11: Notes
P01 | Revit families for structural scope | PT01 | T030-01,T030-02 |  | 2 | Outstanding | bar: 2026-01-11
P02 | Project template file | PT02 | T010-02 |  | 1 | Outstanding | bar: 2026-01-11
P03 | Shared coordinates confirmed | PT03 | T010-03 |  | 1 | Outstanding | bar: 2026-01-11
P04 | Point cloud for existing structure | PT04 | T020-02 |  | 2 | Outstanding | bar: 2026-01-11
P05 | Architectural ceiling void zones confirmed | PT06 | T030-04 |  | 4 | Outstanding | bar: 2026-01-11
P06 | Clash rule matrix agreed | PT10 | T110-02 |  | 8 | Outstanding | bar: 2026-01-11
P07 | Drawing list and titleblock | PT11 | T040-01 |  | 3 | Outstanding | bar: 2026-01-11
TABLE 3 - WAITING ON / BLOCKED LOG | bar: 2026-01-11 to 2026-01-18
Log ID | Week (W no) | Task ID | Status raised | Reason | Waiting on (R code / party) | Raised date | Expected clear date | 2026-01-11: Cleared date; 2026-01-18: Notes
Note on A8: T + category number + sequence, e.g. T030-01 sits under category C030. Reusable as a 4D WBS code.
Note on D8: KEEP GENERIC. Sent to the AI. 'Draft model - substructure', not a real site name.
Note on E8: Optional rough size, default 1. Without it a one-hour task counts the same as a week's modelling.
Note on F8: Regular = agreed at kickoff. Additional = added later; fill in Date added.
Note on H8: The week number you expect this finished. Without it nothing can be reported as late.
Note on I8: Upper row is the week number, this row is the date the week ENDS. Overwrite with your real dates and add columns to the right as the job runs.
Note on AI8: Fill in when the task is done. The app cross-checks this against the week columns and flags any disagreement.
Note on AL8: Prerequisite IDs from Table 2 below, comma separated. e.g. P01,P04
Note on AM8: Task IDs this one cannot start before, comma separated. e.g. T030-01,T030-02
Note on A70: Give each prerequisite a P number for this site. Reference these IDs in the 'Prerequisite (P IDs)' column of Table 1.
Note on A87: Every time you put Blocked or Waiting on in a week cell in Table 1, add a row here saying why. This table is where the bottleneck report comes from - without it the app can only say 'something is stuck', not what.

## A-03
SITE A-03
Site code | Start date | Target submission | Coordinator | Package | Wave
A-03 | 2026-03-02 | 2026-05-29 | R6 | Model only | Wave 2
Keep task and prerequisite names generic - they are sent to the AI. Statuses: Not started / WIP / Blocked / Waiting on / Finished / N/A
TABLE 1 - TASK LIST AND WEEKLY STATUS
[8 empty] | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
Task ID | Category | Discipline | Task / component | Weight | Type | Date added | Target week | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | Completed - week | Completed - date | Responsible (R code) | Prerequisite (P IDs) | Depends on (Task IDs)
C010 | Initial setup | All | [Category] Initial setup
T010-01 | Initial setup | All | Create project folder and CDE structure | 1 | Regular
T010-02 | Initial setup | All | Apply project template file | 1 | Regular
T010-03 | Initial setup | All | Set shared coordinates and survey point | 1 | Regular
C020 | Prerequisite preparation | All | [Category] Prerequisite preparation
T020-01 | Prerequisite preparation | All | Confirm Revit families available for scope | 1 | Regular
T020-02 | Prerequisite preparation | All | Confirm base survey / point cloud usable | 1 | Regular
T020-03 | Prerequisite preparation | All | Confirm reference drawings received | 1 | Regular
T020-04 | Prerequisite preparation | All | Confirm standards and naming convention issued | 1 | Regular
C030 | Draft Modelling | All | [Category] Draft Modelling
T030-01 | Draft Modelling | Struct | Draft model - substructure | 1 | Regular
T030-02 | Draft Modelling | Struct | Draft model - superstructure | 1 | Regular
T030-03 | Draft Modelling | Arch | Draft model - architectural envelope | 1 | Regular
T030-04 | Draft Modelling | MEP | Draft model - MEP primary routes | 1 | Regular
C040 | Draft sheet work | All | [Category] Draft sheet work
T040-01 | Draft sheet work | All | Set up sheets and views | 1 | Regular
T040-02 | Draft sheet work | All | Draft general arrangement sheets | 1 | Regular
C050 | Initial Design | All | [Category] Initial Design
T050-01 | Initial Design | All | Develop design option | 1 | Regular
T050-02 | Initial Design | All | Internal design review | 1 | Regular
T050-03 | Initial Design | All | Issue design for comment | 1 | Regular
C060 | Design Revision | All | [Category] Design Revision
T060-01 | Design Revision | All | Receive and log design revision | 1 | Regular
T060-02 | Design Revision | All | Assess revision impact on model and sheets | 1 | Regular
T060-03 | Design Revision | All | Issue revised design information to team | 1 | Regular
C070 | Modelling Revise | All | [Category] Modelling Revise
T070-01 | Modelling Revise | All | Update model to developed design | 1 | Regular
T070-02 | Modelling Revise | All | Implement design revision in model | 1 | Regular
T070-03 | Modelling Revise | All | Add secondary elements | 1 | Regular
C080 | Sheet work Updates | All | [Category] Sheet work Updates
T080-01 | Sheet work Updates | All | Update sheets to revised model | 1 | Regular
T080-02 | Sheet work Updates | All | Update annotation and dimensions | 1 | Regular
T080-03 | Sheet work Updates | All | Update revision clouds and revision schedule | 1 | Regular
C090 | Other Deliverables preparation | All | [Category] Other Deliverables preparation
T090-01 | Other Deliverables preparation | All | Produce schedules | 1 | Regular
T090-02 | Other Deliverables preparation | All | Produce quantity extract | 1 | Regular
C100 | Final Tuning of individual discipline deliverables | All | [Category] Final Tuning of individual discipline deliverables
T100-01 | Final Tuning of individual discipline deliverables | All | Discipline self-check and cleanup | 1 | Regular
T100-02 | Final Tuning of individual discipline deliverables | All | Purge and audit model | 1 | Regular
C110 | Cross Discipline check | All | [Category] Cross Discipline check
T110-01 | Cross Discipline check | All | Federate models | 1 | Regular
T110-02 | Cross Discipline check | All | Run clash detection | 1 | Regular
T110-03 | Cross Discipline check | All | Clash review meeting | 1 | Regular
C120 | Cross discipline check comments update | All | [Category] Cross discipline check comments update
T120-01 | Cross discipline check comments update | All | Resolve priority 1 clashes | 1 | Regular
T120-02 | Cross discipline check comments update | All | Re-run clash detection | 1 | Regular
C130 | QA | All | [Category] QA
T130-01 | QA | All | Model standards audit | 1 | Regular
T130-02 | QA | All | Drawing check | 1 | Regular
T130-03 | QA | All | Sign off QA checklist | 1 | Regular
C140 | Comments update | All | [Category] Comments update
T140-01 | Comments update | All | Log received comments | 1 | Regular
T140-02 | Comments update | All | Update model and sheets for comments | 1 | Regular
T140-03 | Comments update | All | Return commented log | 1 | Regular
C150 | Submission | All | [Category] Submission
T150-01 | Submission | All | Export and package deliverables | 1 | Regular
T150-02 | Submission | All | Issue transmittal | 1 | Regular
TABLE 2 - PREREQUISITES FOR THIS SITE | bar: 2026-01-11
Prereq ID | Prerequisite | From template (PT ID) | Needed for (Task IDs) | Provided by (R code / party) | Required by week | Status | Date received | 2026-01-11: Notes
P01 | Revit families for structural scope | PT01 | T030-01,T030-02 |  | 2 | Outstanding | bar: 2026-01-11
P02 | Project template file | PT02 | T010-02 |  | 1 | Outstanding | bar: 2026-01-11
P03 | Shared coordinates confirmed | PT03 | T010-03 |  | 1 | Outstanding | bar: 2026-01-11
P04 | Point cloud for existing structure | PT04 | T020-02 |  | 2 | Outstanding | bar: 2026-01-11
P05 | Architectural ceiling void zones confirmed | PT06 | T030-04 |  | 4 | Outstanding | bar: 2026-01-11
P06 | Clash rule matrix agreed | PT10 | T110-02 |  | 8 | Outstanding | bar: 2026-01-11
P07 | Drawing list and titleblock | PT11 | T040-01 |  | 3 | Outstanding | bar: 2026-01-11
TABLE 3 - WAITING ON / BLOCKED LOG | bar: 2026-01-11 to 2026-01-18
Log ID | Week (W no) | Task ID | Status raised | Reason | Waiting on (R code / party) | Raised date | Expected clear date | 2026-01-11: Cleared date; 2026-01-18: Notes
Note on A8: T + category number + sequence, e.g. T030-01 sits under category C030. Reusable as a 4D WBS code.
Note on D8: KEEP GENERIC. Sent to the AI. 'Draft model - substructure', not a real site name.
Note on E8: Optional rough size, default 1. Without it a one-hour task counts the same as a week's modelling.
Note on F8: Regular = agreed at kickoff. Additional = added later; fill in Date added.
Note on H8: The week number you expect this finished. Without it nothing can be reported as late.
Note on I8: Upper row is the week number, this row is the date the week ENDS. Overwrite with your real dates and add columns to the right as the job runs.
Note on AI8: Fill in when the task is done. The app cross-checks this against the week columns and flags any disagreement.
Note on AL8: Prerequisite IDs from Table 2 below, comma separated. e.g. P01,P04
Note on AM8: Task IDs this one cannot start before, comma separated. e.g. T030-01,T030-02
Note on A70: Give each prerequisite a P number for this site. Reference these IDs in the 'Prerequisite (P IDs)' column of Table 1.
Note on A87: Every time you put Blocked or Waiting on in a week cell in Table 1, add a row here saying why. This table is where the bottleneck report comes from - without it the app can only say 'something is stuck', not what.